MINUTES & NOTES ON

CTI CCC1 MEETING, Jakarta

(Reported by CTI Secretariat)

(22-24 May 2008)

DAY 1 (Thursday)

| SESSION #3: SEASCAPES |  |  |
| --- | --- | --- |
| Objectives / High-level Strategy | Decision | Comments |
| Objective #1. Priority seascape programs identified, with investment plans developed and sequenced. By 2010, our six governments will jointly and individually (i) identify a set of “priority seascapes” for prioritized investments during 2010 - 2020; (ii) develop an overall investment plan that outlines investments for individual seascapes; and (iii) develop a plan to sequence seascape program activities, based around the 3 phases of the CTI Plan of Action. - Strategy #1: Rapid assessments of existing seascape programs. By 2010, working closely with seascape program partners, our six governments will complete rapid assessments of existing seascape programs, to identify (i) key short-term measures needed to improve management; along with (ii) required investments and potential investment sources. - Strategy #2: Assessments of potential new seascape programs. By 2012, working closely with a range of partners, our six governments will complete assessments of potential new seascape programs, to determine feasibility and identify possible preliminary steps for a start-up phase. | Accepted with further consultation | Timor-Leste - Needs attention to institutional arrangements for implementation Indonesia - Objective #1, Strategy #1, should be changed to rapid assessment of existing / initiated Seascape Programs - Consideration of “transboundary marine parks” should not prejudice ongoing border negotiations. Malaysia: - Discuss these issues in SSME process - Local community involvement important - Need local consultation |
| Objective #2. “Priority seascapes” fully functional. By 2020, all identified “priority seascapes” will be fully functional, contributing in significant ways to environmentally sustainable development for coastal communities and broader economies dependent upon marine and coastal biological resources. - Strategy #1: Adopt a general “model” for a fully functional seascape program. By 2010, our six governments will jointly adopt a set of “Key Elements of a Fully Functional Seascape Program”, describing a general “model” for a successful program (with more specific elements developed based on local conditions). - Strategy #2: Ongoing, periodic assessments of existing seascape programs. On an ongoing and periodic basis, in cooperation with seascape partners, our six governments will help complete assessments of existing seascape programs, and identify short-, medium-, and long-term measures to improve management and achieve the goals and objectives contained in the CTI Plan of Action. - Strategy #3. Mobilize $100 million of new and additional funding to support “priority seascape” programs. By 2015, our six governments will, combined, mobilize new and additional funding totaling $300 million (?) [indicative number requiring further analysis]—generated from domestic and international funding sources and dedicated to “priority seascape” programs. - Strategy #4: Seascape learning mechanisms. Within and between seascape programs, our six governments will develop / strengthen learning mechanisms for sharing best practices and lessons learned “on-the-ground” (e.g., through Tri-national Committee and sub-committees of the SSME process; annual CT Seascape Conferences, a Seascapes Learning Center for the CT, a network of Seascapes practitioners). | Accepted with further consultation | SI: - Integrated conservation and development that benefit people should be at the heart of Seascape Approach Philippines - Objective #2, Strategy #2 - local govts and stakeholders need to be closely involved in establishing new Seascape Programs - Three additional Seascape areas requiring attention will be: Pacific Seaboard, Northern Luzon and South China Sea - SSME and CTI relationship needs to be clarified - Any Seascape Program has to measure economic, social and political impacts of program. Therefore, need to add an objective that includes economic and social components – “triple-bottom line”. - Impacts of Seascape Programs need to be emphasized. - Seascape Programs need to include fisheries component. Indonesia - Objective #2: add at end of sentence: “to optimize existing Seascape Programs - Need better data for new Seascape Program designation Malaysia - Need more complete data to be able to designate Seascape Programs PNG - We need to measure whether progress is being made on meeting Seascape Program objectives - Livelihood issues need be stressed General Clarification: The timeframe under Objective #2, Strategy #1 is for agreeing to a general model, not for implementing it |

Comments by observers

Walton Family Foundation

- Rather than trying to start new Seascape programs, maybe focus for now on existing Seascape Programs.

Peter Mous

- Seascape Outcome may add an extra level of unnecessary complexity, because it overlaps significantly with other CTI Outcomes. In other words, may not need to be a separate outcome in the CTI Plan of Action.

| SESSION #4: ECOSYSTEM APPROACH TO FISHERIES MGMT |  |  |
| --- | --- | --- |
| Objectives / High-level Strategy | Decision | Comments |
| Objective #1. Region-wide Coastal Communities, Fisheries and Poverty Reduction Initiative (CCFPRI). By 2012, a new region-wide Coastal Communities, Fisheries and Poverty Reduction Initiative (CCFPRI) will be launched, with the aims of reducing poverty and achieving sustainable fisheries through well-financed sustainable development investment programs targeting select coastal areas identified as Poverty and Fisheries Enterprise Zones. By 2020, over $1 billion (?) [indicative number requiring further analysis] in total new and additional investments in the CCFPRI will be mobilized, and significant progress toward achieving poverty reduction and sustainable fisheries will be achieved. - Strategy #1: Map Poverty and Fisheries Enterprise Zones. By 2011, each of our six governments will produce maps with spatially-referenced data denoting locations of Poverty and Fisheries Enterprise Zones that would be targeted under the CCFPRI. - Strategy #2: Design the CCFPRI. By 2012, through a comprehensive set of studies, assessments, planning at appropriate government levels, and investor consultations, our six governments will jointly (and individually) complete the design of a CCFPRI, outlining (i) sustainable development trajectories for a select set of Poverty and Fisheries Enterprise Zones, (ii) specific financing options; and (iii) legal and policy actions needed. - Strategy #3: Mobilize financing for the CCFPRI. Key early steps in mobilizing the necessary financing will include: - Double domestic budget allocations. Each of our governments will significantly expand our own budget allocations to support the CCFPRI, at least doubling current levels by 2012. - Investor forums. Starting in 2010, our six governments will jointly (and individually) organize Investor forums to begin galvanizing investor interest in the CCFPRI. - Regional Sustainable Fisheries Investment Fund. Starting in 2010, our six governments will jointly explore the feasibility of a Regional Sustainable Fisheries Investment Fund directly linked to the CCFPRI. | Accepted with revisions (see comments) | Philippines - Focus on national coastal resources / poverty initiatives first (?) - Regarding the concept of Fisheries and Poverty Enterprise Zones: Philippines has established “mariculture highways” – demonstrations and leading to large-scale investments - When we go back home, we could add more strategies under this Objective Indonesia - CCFPRI must be linked more to EAFM - Need general statement that applies to entire PoA: need to optimize and use existing programs (e.g., SSME, ATSEF) Solomon Islands - Alternative livelihoods needs to be stressed Timor Leste - Strategy #3: doubling domestic budget allocation by 2012 not possible for T-L |
| Objective #2: Strong legislative, policy, and regulatory framework for EAFM. By 2012, all six CT countries will have in place a strong legislative, policy, and regulatory framework built around an ecosystem approach to fisheries management (EAFM), as a key step toward addressing common trans-boundary concerns, such as (i) over-fishing of shared fish stocks, and (ii) by-catch of migratory threatened species. By 2020, all shared commercial fish stocks—including tuna—will be at viable population levels, with annual catch limits based on an EAFM, helping to ensure long-term contributions of pelagic fishery industries to economic growth and employment. - Strategy #1: Review existing legislative, policy and regulatory frameworks. By 2011, each of our six governments will complete comprehensive reviews of existing laws, policies and regulations, and identify needed actions to strengthen these frameworks. - Strategy #2: Commission studies of perverse economic subsidies in the fishery sector. By 2012, each of our six governments will complete in-depth studies of any perverse economic subsidies in the fisheries sector that may be inconsistent with EAFM, including assessments of opportunities for redirection of some funding toward activities that are more directly supportive of EAFM. - Strategy #3: Institutionalize EAFM within the government. By 2012, each of our six governments will “institutionalize” EAFM, including, for example, through such steps as: (i) building EAFM into legal and regulatory regimes; (ii) building EAFM into strategic plans of relevant ministries; (iii) annual reporting of progress toward applying the EAFM paradigm; (iv) requirements to use EAFM projection models as part of stock assessment processes; and (v) establishment of fisheries management committees (or other appropriate bodies) to provide expert advice and analysis. - Strategy #4: Engage the fishing industry in supporting EAFM. Establish or use existing stakeholder forums involving the fishing industry to discuss and promote EAFM: e.g., better understanding of laws and regulations, public-private partnerships to promote uptake of specific fishing gear, certification schemes around improve management standards, etc. - Strategy #5. Implement programs to reduce fishing over-capacity. Develop financial compensation mechanisms, livelihood support programs, and other transitioning measures for reducing fishing over-capacity as needed. - Strategy #6. Improve enforcement of IUU. Accelerate efforts to address IUU, including through greater collaboration between national fishery management agencies and enforcement authorities (such as police and navies), through joint enforcement programs among countries, and through independent on-board observer programs. - Strategy #7. Joint negotiation of fishery access agreements. Two or more countries could jointly negotiate fishery access agreements with fishing nations. | Accepted with revisions (see comments) | Solomon Islands - Communities must be key players - Traditional knowledge important Malaysia - Existing regional cooperation programs should be stressed Timor Leste - For objective, 2012 is too soon for having strong legislative and policy framework in place |
| Objective #3: Sustainable management of shared tuna stocks. By 2012, a new Regional Forum on Tuna Governance will be established and operational, serving as a public-private partnership (PPP) mechanism to develop/promote practical solutions toward sustainable management of shared tuna stocks, helping to ensure long-term contributions of the tuna industry to economic growth and employment; the provisional goal of the Forum will be: by 2020, all shared tuna stocks will be at viable population levels, with annual catch limits based on an EAFM, and with spawning and juvenile growth life stages adequately protected. - Strategy #1: Establish a Steering Committee. By 2010, through joint collaboration, our six governments will help catalyze a Forum Steering Committee to define provisional goals, objectives, and various operational design elements of the Forum, as well as to develop outreach plans to engage a broader set of actors in the Forum - Strategy #2: Identify a host institution and funding for a three-year pilot phase. By 2012, through the Forum Steering Committee, our six governments will identify a host institution and a funding model for a three-year pilot phase of the Forum. - Strategy #3: Mobilize private sector leaders. Initiate dialogue with private sector companies who are most likely to be early adopters of best practices. This can build upon sustainable seafood commitments already made and targets set by some of the world’s largest seafood retailers, such as Wal-Mart and Carrefour. - Strategy #4: Develop/carry out pilot phase agenda. Based on the above assessments, develop and carry out a pilot phase agenda for the Regional Forum. Options for consideration include: - Certification schemes. For example, Marine Stewardship Council certification could be more widely used as a market mechanism to promote best practices in fishing. - Trans-boundary “tuna peace parks” in Sulu Sulawesi Seas and other areas. Under the Regional Forum and through other processes, the concept of “tuna peace parks” could be explored, designed to protect particularly critical spawning and juvenile growth areas. Such a designation might require, for example, new regulations of fishing operations, awareness and enforcement programs, targeted research, and special collaborative arrangements. - New financial compensation mechanism(s) that recognize critical spawning and juvenile growth “services” of key areas within the CT. New financial mechanisms could be explored to compensate fishers and to support conservation measures designed to reduce fishing pressures on tuna spawning and juvenile growth areas within the CT, leading to more reliable, long-term tuna industry revenue flows. - By-catch reduction programs. This could include, for example, programs to promote broad uptake of circle hooks to reduce sea turtle by-catch. - IUU. New surveillance, enforcement, and judicial cooperation measures could be explored. - Agreements in relevant Regional Fisheries Management Organizations (RFMOs). Drawing on more informal discussions in the Regional Forum, agreements on tuna management could be pursued under formal RFMO governmental processes. - Engaging navies, coast guards, and police force in enforcement. New efforts to engage navies in enforcement activities. | Accepted with revisions (see comments) | PNG - Forum Fisheries Agency (FFA) is promoting EAFM in Western Pacific - Need to cross reference these objectives and strategies with existing frameworks Philippines - Should not just cover tuna, but also small pelagics - Need to recognize the principle of country-driveness (“common but differentiated realities”), allowing for countries to proceed at their own pace. - Regional Forum on Tuna Governance – take into account Central and Western Pacific Tuna Commission. Go beyond just a “forum” (which suggests just talking) and develop creative mechanisms that can catalyze practical actions (e.g., regional trading “floor” promoting sustainable fisheries trade). - Objective #2. Strategy #2 on perverse subsidies. Is this limited to just CT6 countries or should it also cover subsidies by countries with distant water fishing fleets (e.g., poaching in SSME). Indonesia - Instead of a new regional forum on tuna, create a CT countries working group on tuna governance in collaboration with existing RFMO - For Strategy #4, “transboundary peace park” not yet considered by Govt of Indonesia |
| Objective #4: Sustainable Live-Reef Food Fish Trade (LRFT). By 2012, a Regional Forum on the Live-Reef Food Fish (LRF) Trade will be established and operational, serving as a public-private partnership (PPP) mechanism to develop / promote practical solutions designed to achieve a more environmentally sustainable trade and to generate long-term economic and livelihood benefits, especially for coastal communities; provisional goals are: (i) by 2020, a 50% reduction—across the CT—in destructive fishing practices linked to the LRF trade (baseline year: 2012); and (ii) by 2020, for identified “LRF hotspots” with significant sourcing of reef fish for the LRF trade, 50% of the populations of targeted species will be at sustainable levels. Affiliated National and Sub-national Forums on the LRF trade will also be established, to advance more localized solutions for “LRF hotspots”. Possible high-level strategies - Strategy #1: Establish a Steering Committee. By 2010, through joint collaboration, our six governments will help catalyze a Forum Steering Committee to define provisional goals, objectives, and various operational design elements of the Forum, as well as to develop outreach plans to engage a broader set of actors in the Forum. - Strategy #2: Identify a host institution and funding for a three-year pilot phase. By 2012, through the Forum Steering Committee, our six governments will identify a host institution and a funding model for a three-year pilot phase of the Forum. - Strategy #3: Assessments of past and current efforts. Commission in-depth assessments of the extensive past and current efforts to address the LRF, covering, for example: - Demand-side strategies, including assessment of opportunities to promote consumer demand for certified sustainable fish supplies. - Supply-side strategies, such as assessments of opportunities (i) to expand mariculture of targeted reef fish (in order to reduce pressures on wild-caught fish and associated reefs); (ii) to introduce certification schemes at the local level; and (iii) to reduce the use of destructive fishing practices. - Strategy #4: Conduct a “systems analysis”. Commission analyses of the “LRFT system” using proven systems analysis tools that identify economic drivers, key actors and their linkages, etc. - Strategy #5: Develop / carry out pilot phase agenda. Based on the above assessments, develop and carry out a pilot phase agenda for the Regional Forum. | Accepted with revisions (see comments) | Indonesia - Should be expanded to sustainable trade of live-reef fish and other organisms |

Comments by observers

WCS

- Objective #2, Strategy #1 – it should not be limited to just reviewing legislation, “reform legislation as needed: should be added

World Fish Center

- Alternative livelihoods needs more emphasis

- Objective #1, Strategy #2, add (iii) alternative income strategies, including potential for aquaculture and mariculture to reduce pressure on wild caught stocks.

- Objective #2, Strategy #2:  should address not just perverse subsidies, but economic constraints more generally

Walton Family Foundation

- Overfishing and destructive fishing need to be emphasized more explicitly in this section, perhaps through adding a separate objective on this.

- Application of EAFM in the context of small-scale coastal fisheries needs to include no-take areas (“no-take replenishment zones”)

Shamus

- Need strategy on coral reefs and coral reef fisheries management plan

- Data collection and some central information exchange useful

NOTES ON DAY 2

(23 May 2008)

| SESSION #5: MPA |  |  |
| --- | --- | --- |
| Objectives / High-level Strategy | Decision | Comments |
| Objective #1. Coral Triangle Heritage Sites System of marine protected areas. By 2020, a comprehensive, ecologically representative, fully functioning, and region-wide Coral Triangle Heritage Sites System of marine protected areas will be in place—covering at least 20% of the critical marine and coastal habitats across the Coral Triangle and designed in ways that significantly improve the income, livelihoods and food security of coastal communities, and conserve the region’s rich biological diversity. - Strategy #1: Establish overall goals, objectives and operational design elements for a CT Heritage Sites System. By 2010, our six governments will jointly agree on overall goals, objectives, designation processes, coordination mechanisms, and other operational design aspects of a region-wide CTHS System, drawing on the most relevant existing processes and Networks (e.g., SSME tri-partite agreement, World Heritage Sites Network and ASEAN Heritage Sites Network, UNESCO Man and Biosphere Reserve Network). - Strategy #2: Complete and endorse the first iteration of a comprehensive map of the CT Heritage Sites System. By 2011, our six governments will jointly complete and endorse a map delineating a region-wide CT Heritage Sites System, based on (i) extensive biophysical and socio-economic data analysis and geographic prioritization, (ii) science-based requirements for sustainable management of marine and coastal resources, and (iii) extensive in-country consultation processes. Special collaboration and external assistance from leading institutions will be required to analyze key issues not addressed in previous mapping exercises, such as spatial mapping of (i) fisheries-based food-security data; and (ii) poverty data overlaid with data on climate change vulnerability of marine ecosystems. Such data sets/maps would be used to help identify candidate MPA sites & networks. - Strategy #3. Establish an MPA Innovations Program and associated MPA Innovations Learning Network. By 2010, each of our six governments will designate a small set of “MPA Innovation Sites and Programs” in our countries representing innovations being piloted for broader replication. Examples of such innovations could include: new approaches to co-management; “MPA campaigns” to raise local community awareness; local community benefit-sharing models; effective enforcement models (e.g., community self-enforcement, arrest/prosecution protocols); models in which MPAs serve as economic engines for local economies; self-financed MPA sites; and programs to scale up sustainable livelihoods around MPAs. By 2010, our six governments will jointly establish and put into operation an “MPA Innovations Learning Network” that proactively shares information and connects practitioners. Learning networks will operate at national and regional levels, and focus primarily on meeting practical, on-site needs. - Strategy #4: Help establish and operationalize a regional Coral Triangle Partnership Fund (CTPF), complemented by domestic funding mechanisms. By 2012, our six governments—in collaboration with multiple donors and other partners—will jointly help establish and put into operation a large-scale region-wide CTPF, with highly streamlined operations and world-class standards built into its design. As a preliminary target, the CTPF should, over time, provide 50% of the recurrent annual costs to effectively manage the region-wide CTHS System—potentially drawing on both sinking and permanent endowment funds, as well as “revolving” funds (periodic replenishment of part of CTPF). A window within the CTPF, or perhaps a sister fund, could emphasize sustainable livelihoods and food security programs for coastal communities, directly linked to MPA management. Each of our six governments will provide an agreed level of “domestic funding” as co-financing to complement this international funding, based on country-specific capacities. Such domestic funding will include, for example, national budget allocations and tourism-based fee systems. - Strategy #5: Establish a special Forum for the Tourism and Travel Industry. Given the direct benefits that flow to the tourism and travel industry from MPAs, a special forum of major companies in this industry will be established by 2012, focused on mobilizing new private sector financial support for MPAs, as well as best practices. - Strategy #6: Establish, strengthen and operationalize Capacity-leap Programs. By 2012, in collaboration with partners and building on existing institutions, our six governments will jointly and individually establish, strengthen and put into operation a set of long-term capacity building programs and institutions. These will be designed to achieve a dramatic leap forward, in the coming decade, in the capacity to manage marine and coastal resources in the CT. Such programs and institutions will be designed to have long-term viability and impacts on broad geographical scales, servicing both government and non-governmental actors, with a primary focus on meeting practical, field-level management needs. One option to be explored would be the need for some type of Coral Triangle Center for Marine Protected Areas, providing regional services such as targeted training programs and technical assistance to a range of capacity-building institutions and individuals across the region. - Strategy #7: Achieve sustainable financing for all CT Heritage Sites. By 2020, each of our governments will take the necessary actions to ensure that all of the CT Heritage Sites within our countries have full financing in place, drawing on a diversity of funding sources and strategies (e.g., Strategies #4 and #5 above, national budget allocations, trust funds, etc.). - Strategy #8: Track progress and achieve effective management across the entire CT Heritage Sites System. By 2012, our six governments will jointly adopt & operationalize a well-defined monitoring program to assess management effectiveness over time of CT Heritage Sites / networks, drawing on active participation of scientific and research institutions and the many existing methodologies. By 2015, 50% of the CT Heritage Sites within each country and across the entire System will meet minimum management effectiveness standards. | Requires further analysis and consideration | PNG - Traditional knowledge should be taken into consideration, also need to balancing the use of the resources that support livelihood of the community. - MPA sometimes involve close/open areas but it needs some guidance so it still support livelihoods of communities. Solomon Islands - Strongly agree to these strategies. - Strategy #4: Support the strategy because it could provide needed sustainable financing aspects for the sites - Tourism fees – SI still struggling with tourism industry development. Need to add possibility for tourism investment. - Strategy 4: might be good to include PES; might require new policies and laws, and analyses - Governments should increase domestic funding for CT Heritage sites, which would send good signals to funding agency Malaysia - Can not make any commitment for any transbounday system, need to clarify definitions of MPAs - Need to address this within the country. States in Peninsular and Sabah have different definition of MPAs - What are main purposes of CT Heritage sites Philippines - Seeks clarification of definition of CT Heritage sites system - compare to World Heritage and ASEAN Heritage sites system - Trust fund very important topic. How it can be operationalize? Indonesia - Need to recognize existing terminology (World Heritage, ASEAN Heritage). Suggest to use other name - It is in the process to develop a National Plan of Action for MPA. Therefore, it can not make a different system specific only for CT region in country. Timor-Leste - Need assistant to conduct stock assessment on fish resources and turtles Indonesia - Change objective CT Heritage System to MPAs & MPA Networks Philippines - Change it to “Network” Timor Leste - Agree to change “Heritage” to “Network. Achieving Heritage system in 10-20 years should be put into one of strategy Have to refer to SOM1 agreement. PNG - Agrees to delete term “Heritage System” to “MPA Network” - How do we draw lessons learned from existing MPAs Solomon Islands - Agreed to use term MPA Philippines - Strategy 3 and 4: Apo Island experience is relevant - Objectives and strategies should highlight more need to demonstrate linkages between MPAs and human well-being. - Evaluate and implement PES - Add strategy: To formulate, implement and monitor a strategy that clearly demonstrates linkages between MPAs & MPA Networks with human well being Decisions: - Replace Obj #1 with more generic: MPA and MPA network established/effectively managed - Obj #1 should be last Strategy (2020) - Additional strategy: assessment of socio-economic benefits of MPAs - Ensure the 20% target in the document with other international convention on related subject. - Strategy #4: stress more in a scoping assessment for possible sustainable funding mechanism in general |

Comments by observers

Peter Mous

- Obj #1:  WSSD and COP7 – agreed to set aside 10% of world oceans as no-take areas 20% of critical in MPAs, of this 30%.  Targets need to be higher to align with int’l commitments

- Obj #1 refers to livelihood and food security.  20-30% of fishing grounds wd then need to be set aside (scientific evidence) There may be a feasibility issue here. Maybe governments could say 10% now, 30% ultimately

USAID

- Population management is a crucial area needing attention (Too many people chasing too few fish)

- Population, health and environment – integrated

- Strategy #3:  Innovations Program and Learning Network (add language that cites programs on pop, health and environment)

Walton Foundation

- Suggest to look again in CBD and World Parks Congress to determine appropriate percentage of MPAs area within the region.  Experts’ suggestion is to set aside 20-30% of fishing grounds as a “no take zone”.  By 2012, 10% area was intermediate goal

- Need to separate best available fisheries science from what is feasible

Kate Newman

Need clear linkage between the five objectives so strategies and action plan could really be integrated as one comprehensive program.

SESSION #6:  CLIMATE ADAPTATION

| SESSION #6: CLIMATE ADAPTATION |  |  |
| --- | --- | --- |
| Objectives / High-level Strategy | Decision | Comments |
| - Objective #1. Region-wide Early Action Climate Adaptation Plan. By 2012, a region-wide Early Action Climate Adaptation Plan for near-shore marine and coastal environments will be completed; by 2015, full implementation of the “no-regret” climate adaptation measures in the Plan will be underway in each CT country, supporting, in particular, economic and livelihood needs of coastal communities that rely heavily on marine and coastal biological resources. (This Plan will serve as a major step toward implementing the climate change adaptation obligations of the CT governments under the UNFCCC.) - Strategy #1: Identify the most important (general) “no-regret” adaptation measures that could be applied across all CT countries, based primarily on analyses of existing models (particularly those developed for marine and coastal ecosystems). By 2011, through commissioned analyses and expert workshops, our six governments will identify general “no-regret” adaptation measures needed in all of our countries in the short-term. As a starting point, a provisional set of “no-regret” measures will include: - Spreading risks to address uncertainties by protecting multiple examples of habitats covering a range of physiographic conditions; - Conserving inherently resilient areas that serve as refuges to reseed affected areas; - Maintaining ecological connectivity – “sources” / “sinks” and functional linkages among associated habitats; - Reducing other non-climate change stresses on marine and coastal ecosystems; and - Building social resilience into adaptation strategies, with a focus on sustainable management of coastal fisheries and livelihood diversification as a response to anticipated future adverse impacts on marine-based livelihoods. - Strategy #2: Identify country-specific measures. By 2012, each of our six governments will identify more country-specific measures needed, as part of our national adaptation strategies being developed under UNFCCC obligations. - Strategy #3. Complete Regional Plan, identify funding, implement Plan. By 2012, our six governments will jointly complete a region-wide Early Action Climate Adaptation Plan for near-shore marine and coastal environments, and identify domestic and international funding to implement the Plan. By 2015, the Plan will be in full implementation in all six CT countries, covering such areas of activity as: demonstration projects in select coastal and small island community settings; legal and policy action; spatial and sectoral planning, guidelines for large-scale investment plans, communications / education and awareness; and science and research. A multi-sectoral forum or committee on this topic in each country may be a useful mechanism to support collaborative and well-coordinated action. | Requires further analysis and consideration | Philippines - Existing Task force on climate change – on mitigation and adaptation - Add strategy about capacity building and training for this new field of interest - Develop baseline data for monitoring purpose - Has renewable energy bill and clean development mechanism. - Develop diagnostic tools to evaluate preparedness for climate change - Why we not put mitigation in the document. - Main impact of climate change is economic - This gives an opportunity for CTI to mainstream itself in the policy debate - CTI can help define components of adaptation for marine environments - This is Ridges-to-Reef. Could be opportunity to influence coastal development - How can we reduce the dependence on natural capital, reduce pressure to allow natural system to regenerate - Climate refugees – saltwater intrusion before submerged lands - Add strategy # 4 Conduct seascape level vulnerability assessments by 2011, a series of seascape level vulnerability assessments will evaluate the immediate impacts of climate change on the biodiversity and human communities of the CT and make recommendations for key site to government level necessary to ensure resilience and implement effective adaptation to changes in the marine environment. - The term “no regret” should come out Malaysia - High-level committee being set up to address climate change issues - Developing database on current status of marine ecosystems across country - Need sharing of information on best practices of adaptation measures - Need to assess future threats Solomon Islands - Capacity is an issue for us - Need training in climate change monitoring - CT MPA networks can have monitoring on climate change impacts PNG - Same comment on need for capacity building - Look beyond coral impacts. Populations on islands are at threat. Need to include strategies on how to relocate island populations where sea level rise impacts. Timor-Leste - Need to integrate all the Convention-related to climate change obligations both in terrestrial as well as in marine Indonesia - Should be less plans and more adaptation strategy - Need to adopt clear strategy first - Why not add mitigation aspect Timor-Leste - We accept these objectives and strategies, but some revisions will be needed - This CCC1 has to produce some substantial output (commitment) - ATSEF must be part of this - Composition of government delegations to CTI meetings need to be consistent for continuity |
| - Objective #2. Networked National Centers of Excellence on Climate Change Adaptation for Marine and Coastal Ecosystems. By 2013, a network of National Centers of Excellence on Climate Change Adaptation for Marine and Coastal Ecosystems will be established and operational in each country; these centers will be designed to (i) improve understanding of future climate change impacts and related issues; and (ii) support comprehensive application of effective adaptation measures to mitigate these impacts. (The centers of excellence will represent important steps toward fulfilling UNFCC obligations of CT governments related to climate change adaptation.) - Strategy #1: Complete comprehensive “business plans” for National Centers of Excellence. By 2012, our six governments will complete comprehensive business plans for the National Centers of Excellence in each of our countries. These business plans will outline: mission, goals, objectives, structural elements, governance, sustainable funding plan, partnerships, etc. Expert workshops of practitioners and scientists will bring together the best minds to help design these Centers. Our governments will share ideas and information to help each other develop solid business plans, and to help ensure such centers are networked effectively. - Strategy #2: Implement a Pilot Phase for National Centers of Excellence. In each of our six countries, our governments will implement Pilot Phases for the National Centers of Excellence, emphasizing a practical national work program, as well as a regional networking component (e.g., sharing models and approaches, collaborating around regional assessments). Wherever possible, we will build upon existing institutions working on climate change and adaptation issues. All of our national centers will have direct connections to relevant line ministries, universities and research institutions, local governments, and other stakeholders that will be involved in implementation of adaptation measures within the country. - Strategy #4. Studies of the economic costs of inaction (including economic benefits of action). For all of these national centers, one of the key initial areas of research will be the economic costs of inaction, to assist decision-makers in decisions related to budgeting and planning. - Strategy #5. Communications strategies. For all of these national centers, another key initial area of work will be developing effective communications strategies. Examples could include: (i) case studies and testimonials of local communities already witnessing and experiencing climate impacts, to help communicate to other local communities and decision-makers the urgency for action; (ii) user-friendly printed and video materials customized for decision-makers; and, (iii) learning networks and other information sharing mechanisms. |  | Indonesia - Prefer to make Network part of Objective# 2 as a strategy PNG - Obj 2: Strat 5. Communication should also cover local communities - Stressed incorporating capacity building into Obj 1 Malaysia - Obj 2: Nat’l Ctr of Excellence – let countries decide if new center needed SI - Obj 2 – include coastal communities as well – as a new strategy |

Other comment from Observer

WWF

Need more specifics in fisheries and species outcomes on climate change

ADB

Need to integrate adaptation more into every other Outcome

Tonny

SOM1 already said do not focus on mitigation

TNC

Map out (model) populations most at risk and where populations are most likely to move to

WWF

Disaster risk reduction key

Lombok advocacy campaign on climate change, vulnerabilities, etc. The local govt decreed a Task Force, drawing on local budget

WCS

Add to “no-regret” (non-“no-regret” activities)

Caleb summary

- Capacity building

- Economic livelihoods and diversification strategies

- Where r the places where people most vulnerable and status of their ecosystems

- Land/sea interface – coastal zone:  least amount of conservation focus. CTI has comparative advantage to address these zones

NOTES ON CCC1 MEETING

Day 3

(24 May 2008)

| SESSION #7: Threatened Species |  |  |
| --- | --- | --- |
| Objectives / High-level Strategy | Decision | Comments |
| Objective #1. Sharks, sea turtles, and cetaceans in CT removed from threatened status list. By 2015, targeted threatened species of sharks, sea turtles, and cetaceans will no longer be declining; by 2020, these species will be removed from the threatened status list, as a key step toward preventing their extinction and supporting healthier overall marine ecosystems. Annotations to Objective #1: - Specific threatened species to be targeted under this objective will need to be determined in the early stage of implementation, but is likely to include, in particular, all five species of threatened cetaceans in the CT, all six species of threatened sea turtles in the CT, and all species of threatened sharks in the CT. - A special focus under this objective will be on the multilateral dimensions to improving the threatened status of these species, addressing such issues as: (i) habitat needs for all life-cycle stages of highly migratory species; (ii) international trade impacts; (iii) international sanctuaries; (iv) international shipping and its impacts on cetaceans; and (v) bycatch related to foreign fishing fleets and fisheries operations across multiple countries in the CT. - Further assessments (e.g., GMSA) and targeted research will help inform early stages of implementation of this objective, including identification of species and geographies requiring priority attention. - Prepare national plan of action for shark management. Possible high-level strategies - Strategy #1: By 2011, our six governments will jointly adopt a region-wide Sharks Conservation Action Plan, identifying the most important measures needed (at the regional and national levels) to improve the status of sharks across the CT—with a particular focus on the following multilateral dimensions: - finning export industry and needed reforms, including addressing supply side issues (shark finning industry) and demand side issues (e.g., mainland China and Hong Kong markets) - shark fisheries for broader consumption, particularly spurred by international trade - enforcement legislation and action on shark fishing and finning, including reducing incidence of IUU catch - targeted collaborative research - incidental bycatch in other fisheries (e.g., longline tuna), including legislative reform and practical modifications of fishing gear - support needed to strengthen the capacity to implement key policy frameworks across all CT countries - Strategy #2: By 2011, our six governments will jointly adopt a region-wide Sea Turtles Action Plan, identifying the most important measures needed (at the regional and national levels) to improve the status of sea turtles across the CT—with a particular focus on the following multilateral dimensions: - transboundary nature of life-cycle stage requirements, migratory patterns, and related protection strategies - international trade in turtle meat and parts - incidental bycatch in other fisheries (e.g., long line tuna), including legislative reform and practical modifications of fishing gear - targeted collaborative research - support needed to strengthen the capacity to implement key policy frameworks across all CT countries (Note: This Strategy will build on and strengthen existing efforts, such as the Indian Ocean and South East Asia Memorandum of Understanding for Marine Turtles, and the tri-national agreement for conservation of turtles in the Bismarck Solomon Seas Ecoregion) - Strategy #3: By 2011, our six governments will jointly adopt a region-wide Cetaceans Conservation Action Plan, identifying the most important measures needed (at the regional and national levels) to improve the status of cetaceans across the CT—with a particular focus on the following multilateral dimensions: - international sanctuaries and enforcement - commercial whaling - international shipping lanes, ship strikes, and noise pollution - incidental bycatch (of forage fisheries) - targeted collaborative research - support needed to strengthen the capacity to implement key policy frameworks across all CT countries - Strategy #4: By 2012, as part of the Global Marine Species Assessment (GMSA), our six governments will support completion of assessments of sharks, sea turtles and cetaceans, and selected invertebrates and plants found in the waters of the CT region. Starting immediately, our six governments will help to direct research and necessary resources to completing the Coral Triangle assessments of targeted threatened species. - Strategy #5: By 2012, each of our governments will have in place effective legislative, policy and regulatory frameworks to protected threatened marine species within our waters. Each of our governments will review, revise and strengthen (as needed) laws and policies on the protection and management of threatened, charismatic and migratory species and their habitats. As part of this strategy, we will share relevant information (e.g., draft and adopted laws), to help enable harmonization of legal and policy frameworks across CT countries. | Requires further analysis and consider-ation | PNG Add a strategy to deal with invasive species that threatened the already endangered species. Solomon Islands Relation of Cultural well being of the people Malaysia - Need to assess turtles and sharks. Enforce the management of turtles and sharks, work with neighbor country, try to stop trade. But as long as there is demand. Enforcement still struggle. Although we have advocate local community not do harm thing and report it but still a big problem Philippines - Philpine-Malaysia bilateral turtlr program the major issue is enforcement.  therefore enforcement needs to be strengthened - Mangrove  adopt IUCN criteria, have already regulation to protect species - Turtles are gardeners of sea grasses. Those species help maintaining the balance in food-chain/cycle Indonesia - The objective is for human well-being, so how protecting endangered species will not collide with economic purpose - Actually in Indonesia few national marine park has program in conserving turtle i.e tagging, breeding, etc - Combine program in other region of Indonesia with CT programs - Poachers are coming from Hainan province in China Timor-Leste - How about country that not include in CT members because the migratory - Need to do cost-benefit analysis on become member of CITES  is there any support for Timor Leste - Have regulations for protecting natural resources, but need other instruments to strengthened in country action |

Comments by observers

USAID

On options  add strategy to strengthened environmental enforcement, build on existing initiatives.  Developing and standardize protocol in environmental enforcement.  Suggest to add strategy # 6 by 2010, CT6 government have adopted and implemented a regional cooperation framework on environmental law enforcement founded on existing regional enforcement network and effective national enforcement bodies.

Continuous enforcement.  CT regions is porous region, threats are coming from many directions

CI

Support USAID, enforcement is very important.  Concentrate on as many trophic level as possible not only for certain species.

Speaker

Agreed to increased enforcement.

Conservation could goes hand-in-hand with tourism and actually could protect livelihood of the community

No points of having all good regulation if we can’t enforce it

Speaker

To ensure the take/harvest is not more than the capacity of reproduction.  We have not have a comprehensive understanding of the life cycle of sharks, turtles and cetaceans. Therefore the cooperation can address this by working together.

Enforcement is difficult, plus corruption. Enforcement should be continuous process because it is not a direct result.  ASEAN Wildlife Enforcement could include CT region.

Need to work in illegal consumer country like China and Taiwan. It will be much more powerful if CT member work together