“ISSUES AND OPTIONS

FOR CTI PLAN OF ACTION”

DECISION DRAFT FOR

DESIGNATION AND MANAGEMENT OF PRIORITY SEASCAPES

CORAL TRIANGLE INITIATIVE (CTI)

ON CORAL REEFS, FISHERIES AND FOOD SECURITY

A technical background document prepared by the CTI Regional Secretariat

to help inform the development of the CTI Plan of Action

(Draft #1; May 14, 2008)

This technical background document, prepared by the Regional CTI Secretariat, is designed to help inform the governmental discussions on the contents of the CTI Plan of Action. In particular, it is being provided at this time to support preparations for the first meeting of the CTI Coordination Committee. The document focuses on the five over-arching goals of the Plan of Action that were agreed at the first Senior Officials Meeting (SOM1): priority seascapes; ecosystem approach to managing fisheries; marine protected areas; climate change adaptation; and threatened species status. For each goal, key issues are summarized, and options for possible objectives and high-level strategies are presented for consideration. This document is designed to serve as a useful starting point for in-depth discussions by the six Coral Triangle governments on the contents of the Plan of Action. The information is structured to help facilitate a systematic approach to building a consensus around the important and complex issues that will be addressed in the Plan of Action.

- OPTIONS FOR CTI PLAN OF ACTION

Based on the background information and key issues analysis, CT governments may wish to consider the following options for inclusion in the CTI Plan of Action.

Objective #1. Priority seascape programs identified, with investment plans developed and sequenced.  By 2010, our six governments will jointly and individually (i) identify a set of “priority seascapes” for prioritized investments during 2010 - 2020; (ii) develop an overall investment plan that outlines investments for individual seascapes; and (iii) develop a plan to sequence seascape program activities, based around the 3 phases of the CTI Plan of Action.

Annotations to Objective #1:

- Priority seascapes will include seascapes within just one country as well as trans-boundary seascapes. Extensive consultations among our governments and key partners will be required to delineate and designate these priority seascapes.

- We will prioritize geographies with existing seascape programs, and likely include some new geography.

- “Priority seascape” designation will help guide external funding, domestic budget allocations & other sources of domestic funding, establishment of partnerships, & governmental policy actions.

- “Priority seascape” designations and investment plans will need to be regularly reviewed, and possibly updated, based on relevant developments.

Possible high-level strategies

- Strategy #1: Rapid assessments of existing seascape programs.  By 2010, working closely with seascape program partners, our six governments will complete rapid assessments of existing seascape programs, to identify (i) key short-term measures needed to improve management; along with (ii) required investments and potential investment sources.

- Strategy #2: Assessments of potential new seascape programs.  By 2012, working closely with a range of partners, our six governments will complete assessments of potential new seascape programs, to determine feasibility and identify possible preliminary steps for a start-up phase.

Objective #2.  “Priority seascapes” fully functional.  By 2020, all identified “priority seascapes” will be fully functional, contributing in significant ways to environmentally sustainable development for coastal communities and broader economies dependent upon marine and coastal biological resources.

Annotations to Objective #2:

- Our six governments will jointly develop a set of “Key Elements of a Fully Functional Seascape Program”, drawing upon experience and lessons learned to date.

- Drawing on these “Key Elements”, existing and new seascape programs will be periodically assessed and updated (as needed), in order to align them with the goals, objectives and strategies contained in the CTI Plan of Action, and in order to achieve seascape-specific objectives.

- Objectives and high-level strategies under the other 4 other goals in the Plan of Action will contribute significantly to achievement of this objective.

Possible high-level strategies

- Strategy #1:  Adopt a general “model” for a fully functional seascape program.  By 2010, our six governments will jointly adopt a set of “Key Elements of a Fully Functional Seascape Program”, describing a general “model” for a successful program (with more specific elements developed based on local conditions).

- Strategy #2:  Ongoing, periodic assessments of existing seascape programs.  On an ongoing and periodic basis, in cooperation with seascape partners, our six governments will help complete assessments of existing seascape programs, and identify short-, medium-, and long-term measures to improve management and achieve the goals and objectives contained in the CTI Plan of Action.

- Strategy #3.  Mobilize $100 million of new and additional funding to support “priority seascape” programs.  By 2015, our six governments will, combined, mobilize new and additional funding totaling $300 million (?) [indicative number requiring further analysis]—generated from domestic and international funding sources and dedicated to “priority seascape” programs.

- Strategy #4:  Seascape learning mechanisms.  Within and between seascape programs, our six governments will develop / strengthen learning mechanisms for sharing best practices and lessons learned “on-the-ground” (e.g., through Tri-national Committee and sub-committees of the SSME process; annual CT Seascape Conferences, a Seascapes Learning Center for the CT, a network of Seascapes practitioners).

- DECISION TO BE TAKEN

After thoroughly examining the issues, national, regional, and international initiatives and commitment for seascape management, all six government take the decision to:

- Accept (either as is, or with revisions that you think are needed)

- Requires further analysis and consideration (with suggestions for specific analysis needed)

- Reject (with explanations summarizing the basis of your objection)

- New idea (new Objectives or new High-level Strategies under existing objectives; these could be written up and circulated at the upcoming CTI Coordination Committee meeting)

Note: To help prepare for the discussions at the upcoming first meeting of the CTI Coordination Committee, each objective and each high-level strategy described above, or new ideas, could be assigned one of above categories by your government.